## MaintenancePlan
Account: | DEKRA Automobil GmbH |  |  | Downloaded at: | 07/08/2020 01:39 PM
Downloaded by: | Otusanya, Oluwadamilola |  |  | Report name: | Maintenance History
Selected Period: | 07/08/2019 - 07/08/2020 |  |  | Summary: | 715 Building ¦ 914 Equipment(s)
Maintenance Visit
Building | Street | City | Equip. ID | Equip. Desc. | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
| Hohe Straße 11 | Düsseldorf | 1008116 | gr. LA | Maintenance Visit 1: Feb 2020; Maintenance Visit 2: Jun 2020; Maintenance Visit 3: Oct 2020
| Bolkerstraße 6 | Düsseldorf | 1008119 | PA | Maintenance Visit 1: Jan 2020; Maintenance Visit 2: Apr 2020; Maintenance Visit 3: Jul 2020; Maintenance Visit 4: Oct 2020
| Hohenzollernstr. 157 | Mönchengladbach | 1010027 | Personenaufzug 10003785 WE1803 | Maintenance Visit 1: 27/01/2020 OK; Maintenance Visit 2: 17/04/2020 OK; Maintenance Visit 3: 29/06/2020 OK; Maintenance Visit 4: 03/07/2020 OK; Maintenance Visit 5: Nov 2020
| Bahnstraße 18 | Mülheim | 1020249 | Personenaufzug | Maintenance Visit 1: 21/04/2020 OK; Maintenance Visit 2: Jul 2020
| Am Wichelshof 33 | Bonn | 1033173 | Personenaufzug | Maintenance Visit 1: 07/01/2020 OK; Maintenance Visit 2: 05/02/2020 OK; Maintenance Visit 3: 05/05/2020 OK; Maintenance Visit 4: 03/06/2020 OK; Maintenance Visit 5: Sep 2020; Maintenance Visit 6: Nov 2020
| Auf´m Hennekamp 50 | Düsseldorf | 1034632 | Personenaufzug WE2340 10016386 | Maintenance Visit 1: 17/04/2020 OK; Maintenance Visit 2: Apr 2020; Maintenance Visit 3: 30/06/2020 OK; Maintenance Visit 4: Oct 2020
| Nordstraße 25 | Düsseldorf | 1036848 | Personenaufzug seil | Maintenance Visit 1: 13/05/2020 OK; Maintenance Visit 2: 01/07/2020 OK; Maintenance Visit 3: Sep 2020; Maintenance Visit 4: Dec 2020
| Helle 5 | Halver | 1043746 | Personenaufzug Haus 5 | Maintenance Visit 1: 22/01/2020 OK; Maintenance Visit 2: 04/05/2020 OK; Maintenance Visit 3: 06/07/2020 OK; Maintenance Visit 4: Oct 2020
| Helle 9 | Halver | 1043747 | Personenaufzug Haus 9 | Maintenance Visit 1: 22/01/2020 OK; Maintenance Visit 2: 04/05/2020 OK; Maintenance Visit 3: 06/07/2020 OK; Maintenance Visit 4: Oct 2020
| Helle 7 | Halver | 1043748 | Personenaufzug Haus 7 | Maintenance Visit 1: 22/01/2020 OK; Maintenance Visit 2: 04/05/2020 OK; Maintenance Visit 3: 06/07/2020 OK; Maintenance Visit 4: Oct 2020
| Ostwall 29 | Krefeld | 1049396 | Personenaufzug | Maintenance Visit 1: 21/02/2020 OK; Maintenance Visit 2: 07/05/2020 OK; Maintenance Visit 3: Aug 2020; Maintenance Visit 4: Nov 2020
| Schwarzbach 21 | Wuppertal | 1088118 |  | Maintenance Visit 1: 04/02/2020 OK; Maintenance Visit 2: 31/03/2020 OK; Maintenance Visit 3: 08/06/2020 OK; Maintenance Visit 4: Aug 2020; Maintenance Visit 5: Oct 2020; Maintenance Visit 6: Dec 2020
| Gathe 78 / Friedrichstraße 33 | Wuppertal | 1096731 | Barmer GEK | Maintenance Visit 1: 20/02/2020 OK; Maintenance Visit 2: 30/04/2020 OK; Maintenance Visit 3: Aug 2020; Maintenance Visit 4: Nov 2020
| Gathe 78 / Friedrichstraße 33 | Wuppertal | 1096743 | Barmer GEK | Maintenance Visit 1: 20/02/2020 OK; Maintenance Visit 2: 30/04/2020 OK; Maintenance Visit 3: Aug 2020; Maintenance Visit 4: Nov 2020
| Gathe 78 / Karlstraße 13 | Wuppertal | 1096746 | Mietshaus | Maintenance Visit 1: 20/02/2020 OK; Maintenance Visit 2: 30/04/2020 OK; Maintenance Visit 3: Aug 2020; Maintenance Visit 4: Nov 2020
| Im Lohauser Feld 63 | Düsseldorf | 1123380 | Personenaufzug - Haus B | Maintenance Visit 1: 28/01/2020 OK; Maintenance Visit 2: 27/04/2020 OK; Maintenance Visit 3: 29/06/2020 OK; Maintenance Visit 4: Oct 2020
| Konrad-Adenauer-Platz 14 | Düsseldorf | 1136649 | Personen-/Lastenaufzug | Maintenance Visit 1: 18/01/2020 OK; Maintenance Visit 2: 13/02/2020 OK; Maintenance Visit 3: 25/05/2020 OK; Maintenance Visit 4: Oct 2020
| Konrad-Adenauer-Platz 14 | Düsseldorf | 1136650 | Personen-/Lastenaufzug | Maintenance Visit 1: 13/02/2020 OK; Maintenance Visit 2: 07/07/2020 OK; Maintenance Visit 3: Jul 2020; Maintenance Visit 4: Oct 2020
| Cloppenburger Weg 44 | Düsseldorf | 1178543 | Standardaufzug | Maintenance Visit 1: 22/01/2020 OK; Maintenance Visit 2: 04/03/2020 OK; Maintenance Visit 3: 04/05/2020 OK; Maintenance Visit 4: 26/06/2020 OK; Maintenance Visit 5: Sep 2020; Maintenance Visit 6: Nov 2020
| Cloppenburger Weg 46 | Düsseldorf | 1178544 | Standardaufzug | Maintenance Visit 1: 24/01/2020 OK; Maintenance Visit 2: 04/03/2020 OK; Maintenance Visit 3: 30/03/2020 OK; Maintenance Visit 4: 26/06/2020 OK; Maintenance Visit 5: 29/07/2020 OK; Maintenance Visit 6: Nov 2020
| Cloppenburger Weg 48 | Düsseldorf | 1178545 | Standardaufzug | Maintenance Visit 1: 24/01/2020 OK; Maintenance Visit 2: 04/03/2020 OK; Maintenance Visit 3: 24/03/2020 OK; Maintenance Visit 4: 26/06/2020 OK; Maintenance Visit 5: 29/07/2020 OK; Maintenance Visit 6: Nov 2020
| Klaumer Bruch 10 | Oberhausen | 1187063 | Personenaufzug | Maintenance Visit 1: 23/01/2020 OK; Maintenance Visit 2: 24/04/2020 OK; Maintenance Visit 3: Sep 2020; Maintenance Visit 4: Dec 2020
| Sonnenwall 85 | Duisburg | 1195719 | Personen- und Lastenaufzug | Maintenance Visit 1: 07/01/2020 OK; Maintenance Visit 2: 09/03/2020 OK; Maintenance Visit 3: Sep 2020; Maintenance Visit 4: Dec 2020
| Sonnenwall 85 | Duisburg | 1195720 | Personen- und Lastenaufzug | Maintenance Visit 1: 09/03/2020 OK; Maintenance Visit 2: 27/04/2020 OK; Maintenance Visit 3: 08/07/2020 OK; Maintenance Visit 4: Dec 2020
| Wertgasse 30 | Mülheim | 1209538 | Personen- / Lastenaufzug Haus D1 | Maintenance Visit 1: 26/02/2020 OK; Maintenance Visit 2: 22/05/2020 OK; Maintenance Visit 3: 09/07/2020 OK; Maintenance Visit 4: Aug 2020; Maintenance Visit 5: Oct 2020; Maintenance Visit 6: Dec 2020
| Broicher Waldweg 95 | Mülheim | 1209539 | Personen- / Lastenaufzug WSU Aufzug B | Maintenance Visit 1: 15/01/2020 OK; Maintenance Visit 2: 27/04/2020 OK; Maintenance Visit 3: 08/06/2020 OK; Maintenance Visit 4: Aug 2020; Maintenance Visit 5: Oct 2020; Maintenance Visit 6: Dec 2020
| Broicher Waldweg 95 | Mülheim | 1209540 | Personen- / Lastenaufzug WSU Aufzug A | Maintenance Visit 1: 27/04/2020 OK; Maintenance Visit 2: 08/06/2020 OK; Maintenance Visit 3: 17/07/2020 OK; Maintenance Visit 4: Aug 2020; Maintenance Visit 5: Oct 2020; Maintenance Visit 6: Dec 2020
| Parsevalstr. 111 | Mülheim | 1209541 | Personen- / Lastenaufzug WSR Bettenaufz. | Maintenance Visit 1: 07/02/2020 OK; Maintenance Visit 2: 03/06/2020 OK; Maintenance Visit 3: 10/07/2020 OK; Maintenance Visit 4: Aug 2020; Maintenance Visit 5: Oct 2020; Maintenance Visit 6: Dec 2020
| Parsevalstr. 111 | Mülheim | 1209542 | Personen- / Lastenaufzug Anl. WSR | Maintenance Visit 1: 07/01/2020 OK; Maintenance Visit 2: 07/02/2020 OK; Maintenance Visit 3: 03/06/2020 OK; Maintenance Visit 4: Aug 2020; Maintenance Visit 5: Oct 2020; Maintenance Visit 6: Dec 2020